## Sheet1
Great Bentley Footpaths
Item | Date Reported | Report Ref No. | Status | Listing on Website | Ease of walking | Hedgerow or path requires clearing (if applicable) | Date ploughed | Dog & waste bin provision | Clear entrance/route signage | Visable please clear up after your dog notice | PRoW Labelled Route | Additional Notes and/or Recomendations
1 | 2024-02-01 | 2897109 | Awaiting inspection - 56 days - Task to check status early April 2024. MG to check this asap | Heckford Road to Colchester Road (A133) | Need to go here | Clear currently | N/A | No | Yes | No | 1 | No path visible across the field + no marker to suggest where to go to the other side of the field.
2 | N/A | N/A | N/A | Sturrick Farm to Colchester Road (A133) | nice easy path to walk along | Clear currently | N/A | No | Yes | No | 2 | N/A
3 | N/A | N/A | N/A | Heckford Road to Sturrick Lane | nice easy path to walk along | Clear currently | N/A | Yes | Yes | Yes | 3 | N/A
4 | N/A | N/A | N/A | Thorrington Road to Great Bentley Road | Nice route when ground is dry | Clear currently | N/A | Yes | Yes | No | 4 | N/A
5 | 2024-02-01 | 2897114 | Awaiting inspection - 56 days - Task to check status early April 2024. MG checked 31.03.24 and no change | Parish Church to Frating Abbey | Clear route as far as the stream bridge then very soggy from there to the crossing and tricky | Footpath signpost in the church yard, by the kissing gate has fallen down, due to wood rotting. | N/A | Yes on The Green | Yes | No | 5 | a)Fix waymark post. b) Photographs to be added to report of damaged post and kissing gate. Issue with Track It System awaiting answer from ECC 7/3.
6 | N/A | N/A | N/A | Clacton Road (B1027) to Thorrington Creek | nice easy path to walk along | Clear currently | N/A | yes | Yes | No | 7 | N/A
7 | 2024-02-01 | a) 2897124 b) 2897128 | a) Plough Road entrance finger post marking requested (2897124). b) Bridleway No. 20 - Footpath No. 8 waymark sign (2897128). Both awaiting inspection - 56 days - Task to check status early April 2024. MG checked 02.04.24 and no change c) Task set up GBPC website content to be checked and revised as needed against ECC footpath listings. Still needs updating - MG | Great Bentley Green to Birch Avenue & continues from Plough Road to St Mary's Road | Only open from Birch Close to Station road at the entrance to Green and across St Mary's field | Clear currently | N/A | Yes | Yes | No | 8 | Plough Road entrance needs to be visible and clearly marked plus maybe update website listing to reflect new route. Also missing direction sign across the field on the new signpost set on the Bridleway.
8 | 2024-02-01 | 2897138 | Awaiting inspection - 56 days - Task to check status early April 2024. MG to check this asap | Hollybush Hill (B1027) to Marsh Farm | Nice route when ground is dry | Clear currently | N/A | Yes | Yes | No | 10 | a) The stile to cross the first field is in bad state and needs repairs. b) Photographs to be added to report of damaged post and kissing gate. Issue with Track It System awaiting answer from ECC 7/3.
9 | 2024-02-01 | 2897139 | Awaiting inspection - 56 days - Task to check status early April 2024. MG to check this asap | Weeley Road to Colchester Road (A133) | Nice route but tricky to acess as 3-400m of national speed limit highway to negotiate first | Clear currently | N/A | No | Ok | No | 11 | A direction sign to be placed asap for last segment of walk. MS checking and photographs to be taken to add to the report.
10 | N/A | N/A | Task set up to revise GBPC website content. Still needs updating | Birch Estate to St. Mary’s Farm | Really nice path | N/A | N/A | N/A | N/A | N/A | 12 | No longer available to access - should be removed from webpage listing.
11 | N/A | N/A | N/A | Plough Road (Ainger’s Green) to Frating Abbey Farm Road | Really nice path | Clear currently | N/A | Yes | Yes | Yes | 13 | N/A
12 | N/A | N/A | N/A | Tye Road to Weeley via Coppice Farm | Need to go here | Clear currently | N/A | No | Yes - at Tye Road only | Yes | 17 | N/A
13 | N/A | N/A | N/A | Dead Lane to Hollybush Hill (B1027) David Gollifer Walk | Need to go here | Clear enough currently but poor path initially from Hollybush Hill entrance | N/A | Yes | Yes | Yes | 19 | N/A
14 | N/A | N/A | N/A | Cinder Path Bridleway to St. Mary’s Farm | Really nice path | Clear currently | N/A | Yes | Yes | Yes | 20 | N/A