## Sheet1
PRoW Labelled Route | Date Reported | Report Ref No. | Status | Listing on Website | Ease of walking | Hedgerow or path requires clearing (if applicable) | Date ploughed | Dog & waste bin provision | Clear entrance/route signage | Visable please clear up after your dog notice | Additional Notes and/or Recomendations
1 | 2024-02-01 | 2897109 | ECC Last Updated 21/2/24 - Issue - ploughing or cropping on prow. An inspector will carry out an initial assessment to determine the next appropriate action, which may include a site visit. This could take up to 56 days. Please continue to check for updates. | Heckford Road to Colchester Road (A133) | Need to go here | Clear currently | N/A | No | Yes | No | No path visible across the field + no marker to suggest where to go to the other side of the field.
2 | N/A | N/A | N/A | Sturrick Farm to Colchester Road (A133) | nice easy path to walk along | Clear currently | N/A | No | Yes | No | A keep your dog on a lead sign has been suggested from the landowner for this path
3 | N/A | N/A | N/A | Heckford Road to Sturrick Lane | nice easy path to walk along | Clear currently - will need cutting back before next report | N/A | Yes | Yes | No | N/A
4 | N/A | N/A | N/A | Thorrington Road to Great Bentley Road | Nice route when ground is dry | Clear currently - will need cutting back before next report | N/A | Yes | Yes | ` | A tree branch is obstructing the path just a few metres in from the Thorrington Road entrance - photo attached_30.04.24
5 | 01/02/2024 + 1/5/24 | 2897114 + 2916191 | Awaiting inspection - 56 days - May 24 ECC: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. | Parish Church to Frating Abbey | Clear route as far as the stream bridge then very soggy from there to the crossing and tricky | Footpath signpost in the church yard, by the kissing gate has fallen down, due to wood rotting. No change currently - 30.04.24. Path adjacent to Rail line will need cutting back before next report | N/A | Yes on The Green | Yes | No | a)Fix waymark post. b) 1/5/24 Photographs added by logging new report and referring to old report of damaged post by kissing gate. (Issue with ECC Track It System where you can't add on to existing report number, you have to create a new report).
7 | N/A | N/A | N/A | Clacton Road (B1027) to Thorrington Creek | nice easy path to walk along | Clear currently | N/A | yes | Yes | No | N/A
8 | 2024-02-01 | a) 2897124 b) 2897128 | a) Plough Road entrance finger post marking requested (2897124). May 24 - ECC: We've carried out an initial assessment of this issue. We are getting more information to decide what action to take. b) Bridleway No. 20 - Footpath No. 8 waymark sign (2897128). May 24 - ECC: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. c) Task set up GBPC website content to be checked and revised as needed against ECC footpath listings. | Great Bentley Green to Birch Avenue & continues from Plough Road to St Mary's Road | Only open from Birch Close to Station road at the entrance to Green and across St Mary's field | Clear currently | N/A | Yes | Yes | No | Plough Road entrance needs to be visible and clearly marked plus maybe update website listing to reflect new route. Also missing direction sign across the field on the new signpost set on the Bridleway. No change currently_30.04.24
10 | 01/02/2024 + 1/5/24 | 2897138 + 2916195 | May 24 ECC: An inspector will carry out an initial assessment to determine the next appropriate action, which may include a site visit. This could take up to 56 days. Please continue to check for updates. (Reported 1 Feb 2024) | Hollybush Hill (B1027) to Marsh Farm | Nice route when ground is dry | Clear currently | N/A | Yes | Yes | No | a) The stile to cross the first field is in bad state and needs repairs. b) 1/5/24 Photographs added by logging new report and referring to old report of damaged stile. (Issue with ECC Track It System where you can't add on to existing report number, you have to create a new report).
11 | 2024-02-01 | 2897139 | Awaiting inspection - 56 days - Check status June 2024 once photos added to a new report and referred to old report. | Weeley Road to Colchester Road (A133) | Nice route but tricky to acess as 3-400m of national speed limit highway to negotiate first | Clear currently | N/A | No | Ok | No | A direction sign to be placed asap for last segment of walk. MS checking and photographs to be taken to add to the report.
12 | N/A | N/A | Task set up to revise GBPC website content. | Birch Estate to St. Mary’s Farm | Really nice path | N/A | N/A | N/A | N/A | N/A | No longer available to access - should be removed from webpage listing.
13 | N/A | N/A | N/A | Plough Road (Ainger’s Green) to Frating Abbey Farm Road | Really nice path | Clear currently | N/A | Yes | Yes | Yes | At the bottom of the 2nd field - the stile is not identifiable from the path so route is unclear_30.04.24
17 | N/A | N/A | N/A | Tye Road to Weeley via Coppice Farm | Need to go here | Clear currently | N/A | No | Yes - at Tye Road only | Yes | N/A
19 | N/A | N/A | N/A | Dead Lane to Hollybush Hill (B1027) David Gollifer Walk | Need to go here | Clear enough currently but poor path initially from Hollybush Hill entrance | N/A | Yes | Yes | Yes | N/A
20 | N/A | N/A | N/A | Cinder Path Bridleway to St. Mary’s Farm | Really nice path | Clear currently | N/A | Yes | Yes | Yes | N/A